## Projects
| Start Wk | End Date | # of Wk | FTE / wk | Status | Andy | Vinod | Frehiwot | Bala | Amulya | Suchi | Janani | Srilekha | Swarnendu
Production Support | 2022-01-03 | 2022-12-30 | 52 | 1.2 | In Progress |  |  |  | 8 | 8 | 16 | 8 | 8 | 8
AD&D Rollout | 2022-01-03 | 2022-12-30 | 52 | 0.3 | In Progress | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2
SLOT-808 AEP Phase III | 2022-01-03 | 2022-07-29 | 30 | 0.5 | In Progress | 2 | 2 |  |  | 8 |  | 8
SLOT-851 Exelon OAuth + CSR SSO + Agentis SSO | 2022-01-03 | 2022-07-29 | 30 | 0.4 | In Progress | 8 | 8
SLOT-527 CNED/ORU OAuth + Ev2 | 2022-01-03 | 2022-05-20 | 20 | 0.5 | In Progress | 10 | 2 |  | 8
SLOT-796 Exelon CEC Easy Open + HEA v2 | 2022-01-03 | 2022-05-20 | 20 | 0.125 | In Progress | 4 | 1
SLOT-968 PGE DER | 2022-02-07 | 2022-05-06 | 13 | 0.65 | In Progress | 16 | 2 |  | 4 |  |  | 2 | 2
SLOT-882 VEC OAuth | 2022-03-14 | 2022-06-03 | 12 | 0.35 | In Progress | 2 | 8 | 4
SLOT-928 Nicore (NICO) Gas - New Logo Standalone | 2022-04-11 | 2022-07-15 | 14 | 0.45 | In Progress | 2 |  | 8 | 8
UTIL - LMI Savings Hub | 2022-04-25 | 2022-06-03 | 6 | 0.3 | In Progress | 4 |  |  |  | 8
SLOT-971 EVER NBA | 2022-04-25 | 2022-06-17 | 8 | 0.65 | In Progress | 2 |  |  |  | 8 |  | 16
SLOT-881 AEP OAuth (6 OpCo's) | 2022-05-02 | 2022-06-03 | 5 | 0.35 | In Progress | 2 | 8 | 4
SLOT-893 GWP DER | 2022-05-02 | 2022-06-03 | 5 | 0.3 | In Progress | 4 |  |  | 4 |  | 4 |  |  | 6
CAP-217 Mid-American NBA | 2022-05-09 | 2022-07-29 | 12 | 0.45 | In Progress | 4 |  | 10 |  | 4
CAP-241 BCE1 SMB Widgets Demo | 2022-05-09 | 2022-06-24 | 7 | 0.3 | In Progress | 4 |  | 8
CAP-187 CNPA/CNPO Rebranding + CIS Migration | 2022-05-23 | 2022-08-05 | 11 | 0.25 | Evaluating |  |  |  | 4 |  |  |  | 6
CAP-42 VNG - New Logo Standalone | 2022-05-30 | 2022-10-14 | 20 | 0.3 | Committed | 2 |  |  |  | 2 |  |  | 8
CAP-269 CNED/ORU Uplight Oauth SSO | 2022-05-30 | 2022-09-30 | 18 | 0.35 | Evaluating | 4 | 10
CAP-253 PGE Bill Guide STAGE Testing | 2022-06-06 | 2022-07-29 | 8 | 0.25 | Evaluating | 2 |  | 8
CAP-259 CNP MS Standalone NO SSO | 2022-06-27 | 2022-08-05 | 6 | 0.25 | Evaluating |  |  |  |  | 2 | 8
CAP-138 COA DER | 2022-10-03 | 2022-12-09 | 10 | 0 | Evaluating
CAP-101 CNED/ORU CIS Migration | 2022-10-03 | 2022-12-09 | 10 | 0 | Evaluating
CAP-113 Exelon 8 OpCo's - Enable Spanish & Chinese | 2022-10-03 | 2022-12-09 | 10 | 0 | Evaluating
CAP-205 AEPO DSS-EM RAT | 2022-10-03 | 2022-12-09 | 10 | 0 | Evaluating
CAP-273 PSE DSS-EM RAT | 2022-10-03 | 2022-12-09 | 10 | 0 | Evaluating
SLOT-678 CPS OAuth | 2022-10-03 | 2022-12-09 | 10 | 0 | TBD
SLOT-879 DUQ OAuth | 2022-10-03 | 2022-12-09 | 10 | 0 | TBD
SLOT-883 Evergy OAuth (2 OpCo's) | 2022-10-03 | 2022-12-09 | 10 | 0 | TBD
SLOT-683 ENMX OAuth + Ev2 | 2022-10-03 | 2022-12-09 | 10 | 0 | TBD
SLOT-908 SMUD Bill Guide Rollout | 2022-10-03 | 2022-12-09 | 10 | 0 | TBD
SLOT-655 RSVL DER | 2022-10-03 | 2022-12-09 | 10 | 0 | TBD
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter the Monday date of the project start week
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter the Friday date when project ends with HyperCare